## Sheet1
Study Startup Checklist for Study Teams
Huron & IRB Applications
1 | If study involves contract, start Huron application. | Reach out to OSP Officer for Guidance
2 | Go to eIRB--create an IRB application and answer WISER determination questions. | Reach out to IRB Administrator for Guidance
Is WISER Required?
3a | If YES, the protocol must be created in WISER and linked to the IRB application using the 4 digit WISER Protocol No. | See page 5 of 'WISER New Protocol Entry' Guide
3b | If NO, a WISER protocol should not be created. OCR will not be involved.
4 | Respond to 'WISER Initial Review/Build of Study Notification' e-mail from CRFA | *Note: this e-mail will be sent by CRFA approximately 1 day after eIRB creation.
4a | Upload draft protocol, draft ICF, FDA documents in eIRB. | See WISER Non-Oncology Protocol Creation Main>Details (pg. 5); Management (pg. 8); Documents/Info. (pg. 13); Treatment (pg. 27); Institution (pg. 34)
4b | Ensure all required PC Console items are complete (e.g. NCT#, Phase, Summary Accrual Info. Only, Multi-site Trial, RC Total Accrual Goal (Upper), Accrual Duration (Months), Administrative Group, Treatment, Institution)
4c | Upload applicable draft documents into WISER (e.g. Draft Sponsor Provided Draft Budget, Draft Clinical Trial Agreement, Ancillary Contract/Memo, CPTs, Internal Budget, Award Letter)
Before you finalize the budget…
5 | Has the CRFA generated a budget export for you to review?
6 | Are any comments in the task list in WISER from the CRFA requesting revisions?
7a | If YES, complete revisions and/or respond to concerns and skip to step 8 and 8a.
7b | If NO, go to WISER Signoff Process (1) below.
8 | Upload any revisions made to the draft budget or draft CTA into WISER and notify CRFA.
8a | If CRFA requested revisions to the ICF, upload revisions made to the draft ICF into eIRB and notify CRFA upon completion.
9 | Return to Step 5.
WISER Signoff Process
1 | You will receive a system-generated notification via outlook that the study is awaiting your signoff in WISER.
2a | Log into WISER using MedCenter credentials and review the Calendar, Medicare Coverage Analysis (MCA), and Financials (via Budget Export) for accuracy. | WISER: Study Team Signoffs pg. 4-8
2b | Review any pending comments in the task list and respond where necessary. If revisions are needed and/or the budget has not been finalized, return to Step 8.
3 | If no changes are needed to the calendar, MCA, or budget, Complete Spec, MCA, and Budget Signoff. | WISER: Study Team Signoffs pg. 9
4 | OSP Officer has uploaded Final Exhibit into WISER.
5 | IRB Initial Approval has been obtained.
6 | OCR has completed OCR Final Exhibit Signoff in WISER.
7 | PI/PI Designee will receive a system-generated notification via outlook that the study is awaiting PI/PI Designee Final Signoff in WISER. Upon PI/Designee Final Signoff, the contract will be sent for signatures and full execution. | WISER: Study Team Signoffs pg. 12
8 | OSP Officer has completed the contract signoff in WISER upon full execution.
9 | Post Award has generated chartfield. CRFA has received the chartfield and completed the chartfield signoff in WISER.
10 | Open study to accrual. | WISER: Protocol Creation pg. 43
10a | If unable to open the study to accrual, put the study 'On Hold'
*For additional information on WISER and Study Start-up Reference Guides, please visit the CTSI's website: https://ctsi.wakehealth.edu/ or contact Amy Porter Dawson (apdawson@wakehealth.edu).